## Sheet1
Online Poker Gantt Chart
CS 401-01 Project
Git Hub rep: https://github.com/Carlosv1232/dealerProj
TASKS/RESPONSIBILITES | Status of Task | People | Starting Date | Due Date | Total days to work on task | Summary of the Task
Built the Server/Client | Working on it | Carlos V | 2020-02-24 | 2020-03-03 | 8 | The beginning of building BOTH the client and server for the online poker. Make sure the connections are build and can have the data transfer, build the needed classes for 'each' player.
Player "Accounts' are created | Working on it | Vanessa T | 2020-03-04 | 2020-03-11 | 7 | sign-up, logins, and saving-up the information,, it would be added to the player class.
Start building the 'MAIN' system of the tournaments | Working on it | Genesis N | 2020-03-12 | 2020-03-19 | 7 | setting up the hierarchy of each hand(for example, a flush would beat a pair.) And has to be randomly generated. and must be unique.
Start building each server room | Working on it | Vanessa T | 2020-03-20 | 2020-03-30 | 10 | This part is the most difficult b/c this is having players playing tournaments so we need the following: 1) have connection in the server, 2) have a voting system, 3) the turn system(bet, fold, check), 4) the poker GUI. *** need to start on the log-in GUI menu.
GUI | Working on it | Genesis N | 2020-03-31 | 2020-04-07 | 7 | Focusing on the GUI part of the project. As in creating the menu, then provide the information to the user, and the balance(money) of the user. We test to see the functions are working, how the server rooms would look like, and the game chat would be.
Poker Tournament simulation | Working on it | Carlos V | 2020-04-08 | 2020-04-15 | 7 | Poker menu is done. We start working on the simulation. Work on the algorithms of betting and the system dictates the winner based by ranking. i.e. the leader is called 'The King' and whoever is it is the winner.
Finishing Touches: the poker tournament | Working on it | Group | 2020-04-16 | 2020-04-23 | 7 | we work on the finishing touches of the project to make sure everything is working. Then we work on the practice mode of the online poker tournament.
Finishing Touches: The project itself | Working on it | Group | 2020-04-24 | 2020-05-01 | 7 | We work on whatever is causing problems in the tasks that we picked to work on, fix any errors there are. If time allows, we try to finish the practice mode during this time, as well as the chat system.
FINAL WEEK | Working on it | Group | 2020-05-02 | 2020-05-11 | 9 | Everything should be done by now and should be working. If we can we can add stuff like a prize rewards system for extra credit.